## Projektplaner
Eventseite inkl. Turnierplaner
WebAnw2 SoSe21; Huber, Maximilian & Giesler, Michael (1 Zeitraum == 1 Tag) |  |  |  |  | Hervorgehobener Zeitraum: |  |  |  | Dauer des Plans | [6 empty] | Tatsächlicher Start | [6 empty] | % abgeschlossen | [6 empty] | Tatsächlich (hinter dem Plan) | [9 empty] | % abgeschlossen (hinter dem Plan)
AKTIVITÄT | START DES PLANS | DAUER DES PLANS | TATSÄCHLICHER START | TATSÄCHLICHE DAUER | PROZENT ABGESCHLOSSEN | ZEITRÄUME
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84
Geschäftsvorschlag vorb. | 1 | 3 | 1 | 3 | 100%
Projektvorstellung, Motivation, Intention | 1 | 1 | 1 | 1 | 100%
Zieldefinition festlegen | 1 | 1 | 1 | 1 | 100%
Abschätzung Projektumfang | 2 | 1 | 2 | 1 | 100%
Grafisch. Prototyp erstellen | 2 | 2 | 2 | 2 | 100%
HTML/CSS Prototyp | 4 | 5 | 5 | 6 | 40%
Grafisch. Prototyp erstellen | 0 | 0 | 0 | 0 | 0%
Placeholder | 0 | 0 | 0 | 0 | 0%
Placeholder | 0 | 0 | 0 | 0 | 0%
Placeholder | 0 | 0 | 0 | 0 | 0%
Placeholder | 0 | 0 | 0 | 0 | 0%
Dynamischer Prototyp | 0 | 0 | 0 | 0 | 0%
Placeholder | 0 | 0 | 0 | 0 | 0%
Placeholder | 0 | 0 | 0 | 0 | 0%
Placeholder | 0 | 0 | 0 | 0 | 0%
Placeholder | 0 | 0 | 0 | 0 | 0%
Placeholder | 0 | 0 | 0 | 0 | 0%
Vorbereitung Präsentation | 0 | 0 | 0 | 0 | 0%
Placeholder | 0 | 0 | 0 | 0 | 0%
Placeholder | 0 | 0 | 0 | 0 | 0%
Placeholder | 0 | 0 | 0 | 0 | 0%
Placeholder | 0 | 0 | 0 | 0 | 0%
Release | 0 | 0 | 0 | 0 | 0%
HTML/CSS Prototyp dynamisch implementieren | 0 | 0 | 0 | 0 | 0%
Placeholder | 0 | 0 | 0 | 0 | 0%
Placeholder | 0 | 0 | 0 | 0 | 0%
Placeholder | 0 | 0 | 0 | 0 | 0%
Placeholder | 0 | 0 | 0 | 0 | 0%